## Sheet1
STLC
Sno | Phase | Input | Activities | Responsibility | OutCome
1 | Test Planning | Project Plan | Identify the resources | Test Lead/Team Lead(70%) | Test Document
| What to test | Functional Requirements | Team Formation | Test Manager (30%)
| How to test |  | Test Estimation
| When to test |  | Preparation of Test Plan
Reviews on Test Plan
Test Plan Sign-off
2 | Test Designing | Project Plan | Preparation of Test Scenarios | Test Lead/Team Lead(30%) | Test Cases Document
|  | Functional Requirements | Preparation of Test cases | Test Engineers(70%) | Traceability Matrix
|  | Test Plan | Reviews on Test cases
|  | Design Docs | Traceability Matrix
|  | Use Cases | Test Cases Sign-off
3 | Test Execution | Functional Requirements | Executiong test cases | Test Lead/Team Lead(10%) | Status/Test Reports
|  | Test Plan | Preparation of Test Report/Test log | Test Engeneers(90%)
|  | Test Cases | Identifing Defects
Build from Development team
4 | Defect Reporting And Tracking | Test Cases | Preparation of Defect Repot | Test Lead/Team Lead (10%) | Defect Report
|  | Test Reports/Test Log | Reporting Defects to Developers | Test Engineers (90%)
5 | Test closure/Sign-Off | Test Reports | Analyzing Test Reports | Test Lead/Test Manager(70%) | Test Summary Reports
|  | Defect Reports | Analyzing Bug Reporting | Test Engineers(30%)
Evaluating Exit Criteria